Step 21 Report

Select the final model by the written rule

Environment: Claude Code (this chat)   |   Completed: 11 October 2026   |   Report version 1 (11 October 2026)

Thesis: Intelligent Power Transformer Fault Diagnosis Using Dissolved Gas Analysis and Machine Learning (MPhil, UMaT)

Abbreviations (such as PD, D1, T1, ppm) and technical terms are explained in the last section of this report.

In short: The final model is Random Forest on feature set F4. It had the highest mean macro-F1 over the 50 cross-validation folds (0.850). The next pipeline, XGBoost on F4 (0.842), was not significantly different (corrected resampled t-test, p = 0.621), so the rule then asks for the simpler of the two; by the order fixed in advance (decision D18) Random Forest is the simpler, so it stays. The choice was made before any test set was opened.

# 1. Purpose of this step

This step chooses, by the rule written in the Analysis Plan before the work began, the one pipeline (inputs, preprocessing and classifier) that will be fitted on all development records and tested once on the three test sets in Step 22.

# 2. Method used

## Approach

A written rule, fixed in the Analysis Plan (Section 5.4) before any data were analysed, chooses the final model from the cross-validation results of Step 20: the pipeline with the highest mean macro-F1 over the 50 outer folds; if it is not significantly better than the next pipeline, the simpler of the two is chosen.

The details the plan left open were fixed in decision D18 while the Step 20 run was still going and before any of its results were read: the 20 candidates are the 5 classifiers x 4 feature sets (the majority baseline is only a reference); significance is judged with the corrected resampled t-test; and the order of simplicity is set in advance.

## Why this method

•  Choosing by a rule written in advance keeps the choice from being fitted to the results, which would make the reported performance too optimistic (Varma and Simon, 2006).

•  Cross-validation folds share most of their training records, so an ordinary paired t-test finds differences too easily; the corrected resampled t-test of Nadeau and Bengio (2003) enlarges the variance to allow for this (Analysis Plan Eq. 28).

•  Preferring the simpler of two equally good models (parsimony) gives a model that is easier to explain, check and maintain in a utility, at no measured cost in accuracy.

## Settings and rules

| Setting | Value |
| --- | --- |
| Candidates | 20 pipelines: logistic regression, SVM (RBF), Random Forest, XGBoost, MLP, each on F1, F2, F3, F4 |
| Score compared | macro-F1 on the 50 outer folds, paired by repeat and fold |
| Test | corrected resampled t-test (Eq. 28), two-sided, alpha 0.05, 49 degrees of freedom; n_test/n_train = 87.80 / 351.20 = 0.250 |
| Simplicity order (D18) | logistic regression < SVM < Random Forest < XGBoost < MLP; then fewer input features (F1 = F2 = 5 < F3 = 8 < F4 = 18) |
| Test sets | not opened (checked by the program before it runs) |

## Equations

t=d1k r+ntestntrainσd2#1

where:

t  –  corrected resampled t statistic, compared with a t distribution with k r - 1 = 49 degrees of freedom

d  –  mean over the 50 folds of the difference in macro-F1 between the two pipelines

σd2  –  variance (sample, n - 1) of those 50 differences

k, r  –  folds per repeat (5) and repeats (10)

ntest, ntrain  –  mean number of held-out and of training records per fold

## Tools and programs

•  06_Python_ML/src/ml/step21_select_model.py (applies the rule; writes model_selection.md and model_selection_tests.csv)

•  tests/test_model_selection.py (hand-computed t value, correction more cautious than the plain paired t-test, simplicity order); scipy.stats for the t distribution

## Method references

[M14] C. Nadeau and Y. Bengio, "Inference for the generalization error," Machine Learning, vol. 52, no. 3, pp. 239-281, 2003. doi: 10.1023/A:1024068626366

[M13] S. Varma and R. Simon, "Bias in error estimation when using cross-validation for model selection," BMC Bioinformatics, vol. 7, art. 91, 2006. doi: 10.1186/1471-2105-7-91

# 3. What was done, step by step

1.  Fixed the details of the rule that the plan left open as decision D18 (candidates, which pipeline is 'next', test settings, order of simplicity), at 21:55 while the Step 20 run was at 750 of 1 200 tasks - before any of its results were read.

2.  Wrote the selection program (step21_select_model.py) and its tests; the program refuses to run if a test set has already been opened.

3.  After Step 20 finished, ran the program on the saved fold results: ranked the 20 candidates by mean macro-F1, tested the best against the next, applied the simplicity order, and compared every candidate with the best as supporting information.

# 4. What we found

## Best and next pipeline

|  | Pipeline | Mean macro-F1 (SD) | Difference to best | t | p |
| --- | --- | --- | --- | --- | --- |
| Best | Random Forest, F4 | 0.850 (0.038) | - | - | - |
| Next | XGBoost, F4 | 0.842 (0.039) | 0.008 | 0.497 | 0.621 |

The difference is not significant (p = 0.621 > 0.05). By the simplicity order of D18, Random Forest (family 3 of 5) is simpler than XGBoost (family 4 of 5), and both use the same 18 inputs; the rule therefore keeps Random Forest on feature set F4.

## Settings most often chosen for the selected pipeline in the 50 outer folds

| Setting (inner-loop choice) | Folds |
| --- | --- |
| {"max_depth": null, "min_samples_leaf": 1} | 22 |
| {"max_depth": null, "min_samples_leaf": 2} | 10 |
| {"max_depth": 10, "min_samples_leaf": 1} | 6 |
| {"max_depth": null, "min_samples_leaf": 5} | 4 |
| {"max_depth": 5, "min_samples_leaf": 1} | 3 |

The settings are chosen again on all development records in Step 22 with the same inner procedure; the table shows how stable the choice was across folds.

## Every candidate compared with the best (supporting information)

| Pipeline | Mean macro-F1 (SD) | Difference to best | t | p | Significantly worse? |
| --- | --- | --- | --- | --- | --- |
| Random Forest, F4 | 0.850 (0.038) | - | - | - | (best) |
| XGBoost, F4 | 0.842 (0.039) | 0.008 | 0.50 | 0.621 | no |
| XGBoost, F3 | 0.833 (0.041) | 0.017 | 0.97 | 0.336 | no |
| Random Forest, F3 | 0.824 (0.036) | 0.026 | 1.48 | 0.145 | no |
| Logistic regression, F3 | 0.821 (0.038) | 0.029 | 1.68 | 0.100 | no |
| Logistic regression, F4 | 0.820 (0.039) | 0.030 | 1.71 | 0.093 | no |
| SVM (RBF), F4 | 0.819 (0.038) | 0.031 | 1.70 | 0.095 | no |
| SVM (RBF), F3 | 0.810 (0.041) | 0.040 | 2.23 | 0.030 | yes |
| Logistic regression, F1 | 0.808 (0.036) | 0.043 | 2.67 | 0.010 | yes |
| Random Forest, F2 | 0.805 (0.041) | 0.045 | 2.86 | 0.006 | yes |
| Neural network (MLP), F4 | 0.805 (0.040) | 0.045 | 1.97 | 0.055 | no |
| SVM (RBF), F1 | 0.804 (0.035) | 0.046 | 2.45 | 0.018 | yes |
| Neural network (MLP), F3 | 0.795 (0.044) | 0.055 | 2.95 | 0.005 | yes |
| SVM (RBF), F2 | 0.794 (0.038) | 0.056 | 3.20 | 0.002 | yes |
| Neural network (MLP), F1 | 0.793 (0.044) | 0.057 | 2.29 | 0.026 | yes |
| XGBoost, F2 | 0.788 (0.041) | 0.062 | 4.14 | 0.000 | yes |
| Random Forest, F1 | 0.773 (0.049) | 0.077 | 3.23 | 0.002 | yes |
| XGBoost, F1 | 0.771 (0.049) | 0.079 | 2.98 | 0.005 | yes |
| Neural network (MLP), F2 | 0.765 (0.032) | 0.085 | 3.86 | 0.000 | yes |
| Logistic regression, F2 | 0.742 (0.045) | 0.108 | 5.09 | 0.000 | yes |

12 of the 19 other pipelines are significantly worse than the best; 7 are not. These 19 comparisons are not corrected for multiple testing and are descriptive only; the formal comparison of all models (Friedman and Nemenyi tests) is Step 30. Every pipeline built only on F1 (log gas values) or F2 (gas percentages) was significantly worse than the best; the pipelines that are not significantly worse all use F3 or F4, the sets that contain the gas ratios and Duval percentages.

# 5. Checks

| Check | Result |
| --- | --- |
| Data version 1.0 unchanged (SHA-256 manifest) | PASS |
| Rule details fixed before the Step 20 results were read (D18, 21:55; results first read after 23:44) | PASS |
| Test sets opened before the choice | No - checked by the program (run_info test_sets_opened = false; no ML test predictions exist) |
| Choice follows the written rule | PASS - made by the program, not by hand |
| Unit tests (test_model_selection.py) and full suite | 4 of 4; 91 of 91 pass |

# 6. Problems and fixes

•  None. One point of interpretation was settled in advance rather than after the results: whether a 'model' means a classifier or a classifier with its feature set. D18 treats each of the 20 classifier-feature set pipelines as a candidate, because the inputs are part of what is deployed.

# 7. Decisions

•  D18 (procedural, within the approved plan): candidates, meaning of 'next', settings of the corrected resampled t-test and the order of simplicity, all fixed before the results were read.

# 8. Files produced

•  07_Experiments/model_selection.md (the choice and its reasons); 07_Experiments/model_selection_tests.csv (every candidate against the best)

•  06_Python_ML/src/ml/step21_select_model.py; 06_Python_ML/tests/test_model_selection.py

# 9. What was achieved

•  The final model was chosen by the written rule: Random Forest on feature set F4.

•  Every candidate was compared with the best on the same 50 folds, so the strength of the choice is visible, not only its result.

•  The choice was made and saved before any test set was opened, as the roadmap requires.

# 10. Record of this step

| Item | Record |
| --- | --- |
| Step | 21 - Select the final model by the written rule |
| Environment | Claude Code (this chat) |
| Completed | 11 October 2026 |
| Status | Done |
| Main inputs | 07_Experiments/2026-10-11_nestedcv_v1/fold_metrics.csv (Step 20) |
| Main outputs | 07_Experiments/model_selection.md; 07_Experiments/model_selection_tests.csv |
| Checks | rule followed by program; details fixed before results were read (D18); test sets opened: no; 91 of 91 tests pass |
| Decisions | D18 (selection details; procedural) |

# 11. Data and sources used in this step

Every dataset, document and file this step used is listed below with its full reference, link and fingerprint (SHA-256, first 16 characters shown). Method references are listed in the 'Method used' section. The complete record, with access dates, licences and full fingerprints, is the Data and Source Register (00_Project_Admin/Step_Reports/Data_and_Source_Register.docx and 03_Data/provenance/data_and_source_register.csv).

| ID | Reference and use in the project | Link, DOI and local file |
| --- | --- | --- |
| DF21 | Produced in Step 20 by step20_nested_cv.py (run 2026-10-11_nestedcv_v1, 21:01-23:44, 6 workers). Use: Chosen setting, inner score and all Section 6 measures of every outer-fold task (6 models x 4 feature sets x 50 folds). | File: 07_Experiments/2026-10-11_nestedcv_v1/fold_metrics.csv; SHA-256 5215981A5636EF1E... |
| DF22 | Produced in Step 20 by step20_summarize.py from DF21. Use: Mean and SD over 50 outer folds of macro-F1 and secondary measures, per-class F1, average rank. | File: 11_Results/tables/T4_4_cv_results.csv; SHA-256 B7D7454BDE778667... |
| DF23 | Produced in Step 21 by step21_select_model.py from DF21, applying the Analysis Plan rule with decision D18. Use: Corrected resampled t-test of every candidate against the best; the chosen pipeline (Random Forest, F4). | File: 07_Experiments/model_selection_tests.csv; SHA-256 49B632867E5F190D... |
| DF6 | Made in Step 13 from all frozen files. Use: SHA-256 of every frozen file; checked by verify_data_version() before every later step. | File: 03_Data/data_version_1.0.sha256; SHA-256 260EBE0C8921E52C... |
| SW1 | Python 3.12.10 with 55 pinned packages (06_Python_ML/requirements.txt). Use: Runs every data-preparation, statistics and checking program. | https://www.python.org/downloads/release/python-31210/; File: 06_Python_ML/requirements.txt; SHA-256 594BC0CB122EED99... |

# 12. How this helps the next steps

Next step: Step 22: tune and fit Random Forest on feature set F4 on all development records and predict the internal test set, the IEC TC 10 benchmark and the Li 2019 set - once, with a log showing that the test sets were opened only then.

•  Step 22 tunes the chosen pipeline once more on all 439 development records (same inner procedure), fits it, and predicts the internal test set, the IEC TC 10 benchmark and the Li 2019 set once.

•  The comparison table feeds the discussion in Chapter 4 and the Friedman and Nemenyi tests of Step 30.

# 13. Open items and limitations

•  'Not significantly different' is not proof that two models are equal; with 50 folds, differences of about 0.01 to 0.03 in macro-F1 cannot be resolved.

•  The rule compares only the best and the next pipeline, as written. Besides the next, 6 more pipelines are not significantly worse than the best (no correction for multiple comparisons), including simpler ones such as Logistic regression on F3 (mean macro-F1 0.821, p = 0.100); this is reported as supporting information and does not change the choice.

•  The choice rests on development data whose labelling method is not documented; the inspection-based IEC TC 10 benchmark in Step 22 is the stronger test.

# 14. Abbreviations and terms used in this report

Every abbreviation and technical term that appears in this report is explained below. The fault types follow the definitions of IEC 60599 (clause 5.2). The full list for the whole project is kept in 00_Project_Admin/abbreviations_glossary.csv.

| Abbreviation or term | Meaning | Plain explanation |
| --- | --- | --- |
| MPhil | Master of Philosophy | The research degree this thesis is written for. |
| UMaT | University of Mines and Technology, Tarkwa | The university where the thesis is submitted. |
| DGA | Dissolved Gas Analysis | Measuring the gases dissolved in transformer oil to find faults inside the transformer without opening it. |
| ppm | parts per million | Amount of gas in the oil; 1 ppm = 1 microlitre of gas in 1 litre of oil. |
| H2 | hydrogen | Gas formed mainly by partial discharges (low-energy electrical activity) in the oil. |
| PD | partial discharges | Small electrical discharges that only partly bridge the insulation (corona type, can form X-wax, or small sparking punctures in paper). |
| D1 | discharges of low energy | Sparking or tracking: larger punctures in paper, carbonised paper surface or carbon particles in oil. |
| T1 | thermal fault below 300 °C | Overheating in which the paper has turned brownish. |
| IEC | International Electrotechnical Commission | The world body that publishes electrical standards, such as IEC 60599. |
| IEC TC 10 | IEC Technical Committee 10 (fluids for electrotechnical applications) | The committee that wrote IEC 60599; its database of 117 inspected faulty units is this thesis's main benchmark. |
| ML | machine learning | Computer methods that learn the link between gas values and fault type from labelled examples. |
| SVM | support vector machine | A classifier that separates classes with the widest possible boundary. |
| Random Forest | random forest | Many decision trees, each trained on a random sample; they vote for the answer. |
| XGBoost | extreme gradient boosting | Decision trees built one after another, each correcting the errors of the previous ones. |
| MLP | multilayer perceptron | A small artificial neural network with layers of connected units. |
| Logistic regression | multinomial logistic regression | A simple, explainable model that turns weighted gas values into class probabilities. |
| Benchmark | fixed reference test set | The IEC TC 10 cases whose faults were confirmed by inspection; every method is scored on them. |
| Inspection-based label | fault confirmed by opening the equipment | The fault type was seen by engineers after the unit was opened, not guessed from the gases. |
| Training (development) set | records used to build the models | 439 clean records from the Dissanayake training file. |
| Internal test set | Dissanayake unseen test file | 70 records (61 independent of the benchmark) kept away from training. |
| SHA-256 | Secure Hash Algorithm, 256-bit | A file's digital fingerprint: if one byte of the file changes, the fingerprint changes. |
| Cross-validation | repeated train-and-test on parts of the training data | The data are split into parts; each part is used once for testing while the others train the model. |
| Fold | one part of the cross-validation split | Here the training data are cut into 5 folds (parts). |
| Degrees of freedom | number of classes minus one here | Needed to judge the H statistic (7 classes give 6). |
| CSV | comma-separated values | A plain-text table file that any program can read. |
| docx | Microsoft Word document | The format of these reports. |
| Python | programming language | Used for data preparation, machine learning and statistics (Claude Code). |
| D1-D18 (decisions) | numbered project decisions | Decisions recorded in 00_Project_Admin/decisions_log.md; not the same as the fault codes D1 and D2. |
| Roadmap | the 45-step project plan | Project_Roadmap.docx: every step, its environment and its outputs, done strictly in order. |
| Analysis Plan | Expected Results and Analysis Plan | The approved document that fixes the measures, tests, tables and figures before results are seen. |
| Primary and secondary source | the original document and a document that quotes it | Values from a secondary source are marked TO VERIFY until checked against the primary source. |
| Unit test (matlab.unittest) | Automatic test of one small piece of code | A test that feeds a function a known input and checks the answer, so that any later change that breaks the function is noticed at once. |
| Pipeline | chain of processing steps and a model | Feature building, imputation, scaling and the classifier joined so that they are always fitted together on the same training rows. |
| Feature set (F1-F4) | the inputs given to a model | F1 log gases, F2 gas percentages, F3 log-ratios and Duval percentages, F4 all of them (Analysis Plan 5.1). |
| Nested cross-validation | cross-validation inside cross-validation | The inner loop chooses the settings, the outer loop measures performance on data the tuning never saw. |
| Macro-F1 | average F1 score over the classes | The primary performance measure; every class counts equally however rare it is. |
| SD | standard deviation | How much the 50 fold values spread around their mean; a small SD means the result is stable from fold to fold. |
| F1-score (per class) | harmonic mean of precision and recall | High only when the model both finds the records of a class and is rarely wrong when it names that class. |
| Corrected resampled t-test | test for two models compared on the same folds | A t-test whose variance is enlarged because cross-validation folds share training records (Nadeau and Bengio, 2003; Analysis Plan Eq. 28). |
| Friedman and Nemenyi tests | rank-based comparison of several models | Friedman tests whether models' average ranks over the folds differ; Nemenyi then shows which pairs differ (Step 30). |
| Majority baseline | reference model | Always predicts the most common class; any useful model must do clearly better. |
| Average rank | mean position among the compared models | In every fold the models are ranked by macro-F1 (1 = best); the ranks are then averaged over the folds. |
| RBF | radial basis function | The kernel that lets the SVM draw curved boundaries between classes. |