Step 31A Report

Pre-register Study 2 (exploratory improvement study)

Environment: Claude Code (this chat)   |   Completed: 12 October 2026   |   Report version 1 (12 October 2026)

Thesis: Intelligent Power Transformer Fault Diagnosis Using Dissolved Gas Analysis and Machine Learning (MPhil, UMaT)

Abbreviations (such as PD, D1, T1, ppm) and technical terms are explained in the last section of this report.

In short: At the researcher's request, an exploratory improvement study (Study 2) was planned and fixed in writing before any of its models was trained. It tests three remedies for the dataset shift found in the main study: training on several sources, a hybrid model that also uses the conventional methods' answers, and a reject option. The protocol was fingerprinted at 2026-10-12T16:24:48; the roadmap is now Version 3 with Steps 31A-31F. The main (confirmatory) results are unchanged and remain the thesis's main result.

# 1. Purpose of this step

This step makes sure that Study 2 is planned before it is run, so that its results can be trusted and cannot be tuned to the test sets that were already used.

# 2. Method used

## Approach

Pre-registration: before any Study 2 model was trained, a protocol fixed the questions, the data rules, the three models, the measures, the statistical tests, the reject option and the decision rules. Its SHA-256 fingerprint was recorded with the time, so it can be shown later that the plan came first.

The roadmap was updated to Version 3 (Steps 31A-31F) and the master plan received a Phase 6b; Version 2 of the roadmap was archived unchanged.

## Why this method

•  Once the test sets have been seen, any further improvement risks being fitted to them. Fixing the plan in advance, and labelling the study exploratory, keeps the work honest and publishable.

•  Leave-one-source-out evaluation measures what matters in practice - performance on a data source the model has never seen - and addresses the dataset shift found in Steps 22-31.

•  A reject option (Chow, 1970) lets the model be compared fairly with conventional methods that also give no diagnosis in uncertain cases.

## Settings and rules

| Setting | Value |
| --- | --- |
| Sources (held out in turn) | Dissanayake training, Dissanayake unseen, IEC TC 10 power transformers, Li 2019 |
| Models | A released model; B pooled Random Forest/F4; C hybrid (B + conventional answers, gate flags, boundary distances) |
| Classes | six (T1 and T2 merged, because IEC TC 10 has no separate T1/T2 labels) |
| Statistics | macro-F1 (primary); bootstrap B = 2000; McNemar with Holm; reject option at the coverage of IEC 60599 and Rogers |
| Status | exploratory; the confirmatory results of Steps 22-31 are unchanged |

## Tools and programs

•  00_Project_Admin/report_builder/build_study2_protocol.ps1 (protocol), update_roadmap_v3.ps1 (roadmap Version 3)

## Method references

[M32] C. K. Chow, "On optimum recognition error and reject tradeoff," IEEE Transactions on Information Theory, vol. 16, no. 1, pp. 41-46, 1970. doi: 10.1109/TIT.1970.1054406

[M20] B. Efron and R. J. Tibshirani, An Introduction to the Bootstrap. New York: Chapman and Hall, 1993.

[M29] Q. McNemar, "Note on the sampling error of the difference between correlated proportions or percentages," Psychometrika, vol. 12, no. 2, pp. 153-157, 1947. doi: 10.1007/BF02295996

[M30] S. Holm, "A simple sequentially rejective multiple test procedure," Scandinavian Journal of Statistics, vol. 6, no. 2, pp. 65-70, 1979. https://www.jstor.org/stable/4615733

# 3. What was done, step by step

1.  Checked how the four data sources overlap (known from Step 9, decision D9: Li 2019 contains 115 of the IEC TC 10 cases; the Dissanayake unseen file contains 9) and how Step 10 defined near-duplicates, so that the pooling rules could be written correctly.

2.  Recorded decision D28 and wrote the Study 2 protocol (5 pages): questions, data rules, models, measures, tests, reject option, decision rules, outputs.

3.  Confirmed the reject-option reference (Chow, 1970) in Crossref and fingerprinted the protocol.

4.  Archived roadmap Version 2 and updated the roadmap to Version 3: new Steps 31A-31F in the step overview table and in Stage F; Step 32 now also rebuilds the Study 2 tables and figures. Added Phase 6b to the master plan.

# 4. What was fixed in the protocol

| Item | Fixed choice |
| --- | --- |
| Questions | S2-Q1 pooling; S2-Q2 hybrid; S2-Q3 reject option; S2-Q4 fresh confirmation data |
| Evaluation | leave-one-source-out over four sources; near-copies of held-out records removed from training |
| Deduplication | one copy per exact duplicate; priority IEC TC 10 > Dissanayake training > Dissanayake unseen > Li 2019 |
| Models | A released (unchanged); B pooled Random Forest/F4; C hybrid (B + conventional inputs) |
| Primary measure | macro-F1 over the classes present in the held-out source |
| Decision rule 1 | pooling helps if B - A > 0 (CI excluding 0) on at least 2 of 3 external sources |
| Decision rule 2 | hybrid helps if C - B > 0 (CI excluding 0) on at least 2 of 4 sources |
| Decision rule 3 | reject option competitive if, at IEC 60599's coverage, its accuracy is not below IEC's on at least 2 of 3 external sources |

# 5. Checks

| Check | Result |
| --- | --- |
| Protocol fingerprint matches the recorded value | PASS |
| No Study 2 experiment existed when the protocol was fixed | PASS |
| Confirmatory output DF25 unchanged (11_Results/ml/ml_predictions.csv) | PASS |
| Confirmatory output DF34 unchanged (08_Statistical_Analysis/merged_predictions.csv) | PASS |
| Confirmatory output DF35 unchanged (08_Statistical_Analysis/performance_measures.csv) | PASS |
| Confirmatory output DF37 unchanged (08_Statistical_Analysis/cochran_mcnemar.csv) | PASS |
| Confirmatory output DF39 unchanged (08_Statistical_Analysis/boundary_regression.csv) | PASS |

# 6. Problems and fixes

•  The predicted-class symbol in the protocol's reject-option equation was first drawn incorrectly; the equation was corrected and the protocol rebuilt before its fingerprint was recorded.

# 7. Decisions

•  D28: Study 2 (scope chosen by the researcher; design procedural, fixed before any Study 2 model).

# 8. Files produced

•  00_Project_Admin/Study2_Protocol.docx; 03_Data/study2/study2_protocol.sha256

•  00_Project_Admin/Project_Roadmap.docx (Version 3); 00_Project_Admin/archive/Project_Roadmap_v2_before_Study2_2026-10-12.docx; PROJECT_PLAN.md (Phase 6b)

•  00_Project_Admin/report_builder/build_study2_protocol.ps1, update_roadmap_v3.ps1

# 9. What was achieved

•  Study 2 is pre-registered: protocol fingerprint 3EF4C2855A16C5A9... recorded at 2026-10-12T16:24:48, before any Study 2 model.

•  The roadmap (Version 3) and the master plan include Study 2; the earlier roadmap is archived.

•  The confirmatory result files were checked by fingerprint and are unchanged.

# 10. Record of this step

| Item | Record |
| --- | --- |
| Step | 31A - Pre-register Study 2 |
| Environment | Claude Code (this chat) |
| Completed | 12 October 2026 |
| Status | Done |
| Main inputs | Confirmatory results of Steps 22-31; decisions_log.md |
| Main outputs | 00_Project_Admin/Study2_Protocol.docx; 03_Data/study2/study2_protocol.sha256; Project_Roadmap.docx Version 3; PROJECT_PLAN.md Phase 6b |
| Checks | protocol fingerprint matches; confirmatory outputs unchanged (5 files); no Study 2 experiment yet |
| Decisions | D28 (Study 2: scope by the researcher; design procedural) |

# 11. Data and sources used in this step

Every dataset, document and file this step used is listed below with its full reference, link and fingerprint (SHA-256, first 16 characters shown). Method references are listed in the 'Method used' section. The complete record, with access dates, licences and full fingerprints, is the Data and Source Register (00_Project_Admin/Step_Reports/Data_and_Source_Register.docx and 03_Data/provenance/data_and_source_register.csv).

| ID | Reference and use in the project | Link, DOI and local file |
| --- | --- | --- |
| DF40 | Written in Step 31A (decision D28) before any Study 2 model was trained; fingerprint recorded in 03_Data/study2/study2_protocol.sha256. Use: Fixes the questions, data rules, models, measures, statistics and decision rules of Study 2. | File: 00_Project_Admin/Study2_Protocol.docx; SHA-256 3EF4C2855A16C5A9... |
| DF25 | Produced in Step 22 by step22_final_fit.py with DF24; test sets predicted once (see test_set_access.log). Use: Predicted class and class probabilities for every internal-test, IEC TC 10 and Li 2019 record. | File: 11_Results/ml/ml_predictions.csv; SHA-256 D103E8CA1B21C49A... |
| DF34 | Produced in Step 28 by step28_merge_predictions.py from DF2, DF9 (conventional predictions) and DF25 (ML predictions). Use: True class, flags, ML prediction and probabilities, conventional answers (raw, upper gate, lower gate, merged classes), boundary distances. | File: 08_Statistical_Analysis/merged_predictions.csv; SHA-256 EDB799A2CDA41A69... |
| DF35 | Produced in Step 29 by step29_measures.py from DF34 only (decision D25). Use: Strict and conditional accuracy, coverage (Wilson), macro-F1, balanced accuracy, kappa, MCC (bootstrap) for every method and set. | File: 08_Statistical_Analysis/performance_measures.csv; SHA-256 C86B438A3EF7873F... |
| DF37 | Produced in Step 30 by step30_tests.py from DF21 (fold results) and DF34 (merged predictions); decision D26. Use: McNemar (Holm), Cochran's Q, Friedman/Nemenyi, kappa, hypothesis criteria. | File: 08_Statistical_Analysis/cochran_mcnemar.csv; SHA-256 CCC3414122D688BB... |
| DF39 | Produced in Step 31 by step31_boundary.py from DF34 (decision D27). Use: Logistic regression of ML-method disagreement on boundary distance; criterion 3. | File: 08_Statistical_Analysis/boundary_regression.csv; SHA-256 0CB49CA5E7B168D4... |

# 12. How this helps the next steps

Next step: Step 31B: build the pooled, deduplicated data set with near-duplicate groups and the hybrid inputs, exactly by the protocol's rules.

•  Step 31B builds the pooled, deduplicated data set exactly by the protocol's rules.

•  Steps 31C-31E train, measure and interpret; the decision rules are already fixed, so the interpretation cannot drift towards the results.

# 13. Open items and limitations

•  IEC TC 10 and Li 2019 have already been seen: Study 2 results on them are exploratory and need confirmation on a fresh data set (Step 31F).

•  The protocol merges T1 and T2; Study 2 therefore says nothing about separating those two thermal classes.

# 14. Abbreviations and terms used in this report

Every abbreviation and technical term that appears in this report is explained below. The fault types follow the definitions of IEC 60599 (clause 5.2). The full list for the whole project is kept in 00_Project_Admin/abbreviations_glossary.csv.

| Abbreviation or term | Meaning | Plain explanation |
| --- | --- | --- |
| MPhil | Master of Philosophy | The research degree this thesis is written for. |
| UMaT | University of Mines and Technology, Tarkwa | The university where the thesis is submitted. |
| DGA | Dissolved Gas Analysis | Measuring the gases dissolved in transformer oil to find faults inside the transformer without opening it. |
| ppm | parts per million | Amount of gas in the oil; 1 ppm = 1 microlitre of gas in 1 litre of oil. |
| PD | partial discharges | Small electrical discharges that only partly bridge the insulation (corona type, can form X-wax, or small sparking punctures in paper). |
| D1 | discharges of low energy | Sparking or tracking: larger punctures in paper, carbonised paper surface or carbon particles in oil. |
| T1 | thermal fault below 300 °C | Overheating in which the paper has turned brownish. |
| T2 | thermal fault 300 to 700 °C | Overheating in which the paper has carbonised. |
| IEC | International Electrotechnical Commission | The world body that publishes electrical standards, such as IEC 60599. |
| IEC 60599 | IEC guide to the interpretation of dissolved and free gas analysis | The international standard that defines the fault types and the IEC gas-ratio method. |
| IEC TC 10 | IEC Technical Committee 10 (fluids for electrotechnical applications) | The committee that wrote IEC 60599; its database of 117 inspected faulty units is this thesis's main benchmark. |
| Rogers ratios | older gas-ratio method by R.R. Rogers | A ratio table that names faults from three gas ratios; kept in IEEE C57.104. |
| ML | machine learning | Computer methods that learn the link between gas values and fault type from labelled examples. |
| Random Forest | random forest | Many decision trees, each trained on a random sample; they vote for the answer. |
| Logistic regression | multinomial logistic regression | A simple, explainable model that turns weighted gas values into class probabilities. |
| Training (development) set | records used to build the models | 439 clean records from the Dissanayake training file. |
| SHA-256 | Secure Hash Algorithm, 256-bit | A file's digital fingerprint: if one byte of the file changes, the fingerprint changes. |
| Fold | one part of the cross-validation split | Here the training data are cut into 5 folds (parts). |
| CSV | comma-separated values | A plain-text table file that any program can read. |
| docx | Microsoft Word document | The format of these reports. |
| D1-D23 (decisions) | numbered project decisions | Decisions recorded in 00_Project_Admin/decisions_log.md; not the same as the fault codes D1 and D2. |
| Roadmap | the 45-step project plan | Project_Roadmap.docx: every step, its environment and its outputs, done strictly in order. |
| ND (no diagnosis) | No diagnosis | The answer of a method when no rule applies or a ratio it needs cannot be calculated. It is a result and is never deleted. |
| Boundary distance | Distance to the nearest decision boundary | How far a sample is from the line where the diagnosis would change. A small distance means a small measurement error could change the diagnosis. |
| Feature set (F1-F4) | the inputs given to a model | F1 log gases, F2 gas percentages, F3 log-ratios and Duval percentages, F4 all of them (Analysis Plan 5.1). |
| Macro-F1 | average F1 score over the classes | The primary performance measure; every class counts equally however rare it is. |
| Balanced accuracy | mean of the per-class recalls | The share of each class that is found, averaged over the classes, so a rare class counts as much as a common one. |
| Kappa | Cohen's kappa | Agreement between predicted and true classes after removing the agreement expected by chance: 0 = chance, 1 = perfect. |
| MCC | Matthews correlation coefficient | One score from -1 to 1 that uses the whole confusion matrix; 0 means no better than guessing. |
| Friedman and Nemenyi tests | rank-based comparison of several models | Friedman tests whether models' average ranks over the folds differ; Nemenyi then shows which pairs differ (Step 30). |
| Dataset shift | test data differ from training data | Records from another laboratory, country or labelling practice can follow a different pattern, so a model usually scores lower on them than in cross-validation. |
| Class probability | model's confidence in each class | For every record the model gives a probability for each of the seven classes; they add up to 1 and the largest is the prediction. |
| Bootstrap (stratified percentile) | resampling to get a confidence interval | The records are drawn again at random, with replacement and within each fault class, 2000 times; the middle 95 % of the recomputed values is the 95 % interval (Analysis Plan Section 6.2). |
| Conditional accuracy | correct answers out of the records answered | Looks only at the cases where the method gave a diagnosis (Analysis Plan Eq. 7). |
| Coverage | share of records that get a diagnosis | 1 minus the share of no-diagnosis answers (Analysis Plan Eq. 6); the ML model always answers, so its coverage is 100 %. |
| Wilson interval | confidence interval for a proportion | A 95 % interval for an accuracy or a coverage that works well for small samples (Analysis Plan Eq. 21). |
| McNemar test | paired test of two methods on the same records | Uses only the records where one method is right and the other wrong (b and c); tests whether b and c differ more than chance (Analysis Plan Eqs. 30-31). |
| Cochran's Q | test of several methods on the same records | Tests whether all methods have the same share of correct answers before the pairwise tests (Analysis Plan Eq. 29). |
| Holm correction | adjustment for several tests | Keeps the chance of any false positive among the three comparisons per test set at 5 % (Analysis Plan Eq. 32). |
| Logistic regression (of disagreement) | model for a yes/no outcome | Estimates how the chance that ML and a conventional method disagree changes with the distance to the nearest decision boundary (Analysis Plan Eq. 33). |
| Boundary distance | how far a sample lies from a decision line | For the ratio methods in decades of the ratio, for Duval in percentage points to the nearest zone edge (Analysis Plan Eqs. 9-10). |
| Study 2 | exploratory improvement study | An extra study, planned after the main results, that tests ways to improve the model; reported separately from the main (confirmatory) results. |
| Confirmatory vs exploratory | tested as planned vs looked into afterwards | Confirmatory results test a hypothesis fixed in advance on untouched data; exploratory results come from analyses planned after seeing some results and need confirmation on new data. |
| Pre-registration | writing the plan before the analysis | The questions, data rules, methods and decision rules are fixed and fingerprinted before any result exists, so the analysis cannot be fitted to the results. |
| Leave-one-source-out | testing on a source never seen in training | Each data source is held out in turn; the model is trained on the other sources and tested on the held-out one, which measures how well it transfers to new data. |
| Hybrid model | machine learning plus expert rules | A model that receives the conventional methods' answers and boundary distances as extra inputs besides the gas features. |
| Reject option | the model may decline to answer | The model gives a diagnosis only when its highest class probability reaches a threshold; otherwise it reports no diagnosis (Chow, 1970). |